AfroPHC Strategic and Operational Plan 2021-08-02 DRAFT

The African Forum for Primary Care (AfroPHC) consists of diverse multidisciplinary primary health care (PHC) workforce stakeholders from across Africa.

Our vision is that African PHC service delivery under Universal Health Coverage (UHC) should be comprehensive, accessible, high quality, responsive to local needs, in partnership with communities and delivered by strong teamwork, training and supportive supervision.

Our mission is to bring together the leadership of ALL health workers at the coalface in African primary care and to develop AfroPHC as the voice of the PC/PHC team, sharing resources and supporting each other in building the PHC team for UHC in Africa.

Our five-year objectives for 2021-2025

- Engage and advocate with stakeholders on appropriate PHC human resources and strong PHC teamwork for UHC

- Strengthen socially accountable PHC for communities in Africa

- Support local and country level PHC teamwork across Africa

- Capacitate PHC stakeholders at policy, management, clinical and health level

- Build research and evidence for appropriate PHC human resources and strong PHC teamwork for UHC

- Share information and communicate effectively to strengthen PHC teamwork and UHC across Africa.

- Build AfroPHC as an organization

Annual Operational Plan 2021-2022

What do we expect to see as of 30th March 2022 to say we have advanced each of our objectives? They need to be specific, measurable, appropriate, relevant and time based.

- Engage and advocate with stakeholders on appropriate PHC human resources and strong PHC teamwork for UHC

  - Thirty pan-African and global PHC-related organizations publicly supporting AfroPHC by March 2022.

  - Advisory Board met in October 2021 and February 2022

  - AfroPHC has Non-State Actor Status with WHO by December 2021

  - AfroPHC establish clear liaison with WHO Geneva and WHO AFRO by September 2021

  - AfroPHC actively part of CSEM and related activities by December 2021

  - AfroPHC Youth Wing established by December 2021

- Strengthen socially accountable PHC for communities in Africa

  - Document on “Building PHC Teams for UHC in Africa” submitted to WHO by December 2021

  - Develop plan for PHC guiding documents in Africa by September 2021

- Support local and country level PHC teamwork across Africa

  - Three AfroPHC regions established by March 2022

  - Ten AfroPHC country chapters established by March 2022

- Capacitate PHC stakeholders at policy, management, clinical and health level

  - Ten policy workshops held with various stakeholders by March 2022

  - Four clinical groups established with various key stakeholders by March 2022

  - Twenty weekly CPD meetings held by March 2022

  - One hundred completing the PHC Leadership and Management Course by March 2022

- Build research and evidence for appropriate PHC human resources and strong PHC teamwork for UHC

  - Eight AfroPHC research meetings held by March 2022

  - One AfroPHC grant achieved by March 2022

  - One AfroPHC collaborative research project completed by March 2022

  - The AfroPHC collaborative research platform with twenty practices achieved by March 2022

- Share information and communicate effectively to strengthen PHC teamwork and UHC across Africa.

  - Email communications monthly

  - Google group strengthened with regular contributions from members (SMART?)

  - Press releases issued after all workshops (SMART?)

  - Social media presence widened to improve engagement (SMART?)

  - AfroPHC Conference plan completed by March 2022

- Build AfroPHC as organisation

  - Membership increased to 1000 by March 2022

  - All Executive Board Members chaired a workshop by March 2022

  - All Executive Board Members allocated and supported in a portfolio by September 2021?

  - Funds raised to cover annual budget of $10000 by March 2022

Other ideas

- How to advise African govt on PHC (facilities) and its organization? E.g., netherlands org of PHC who recommend govts.

- Explore joint partnerships with current Supporting Org on shared ideas/projects

- Need rep. on UHC HLM on NCDs – explore partnerships’ around integrated approach

- Political will? E.g., Abuja 15by2015 / Push funding of PHC

- strong country chapters?

- Showcase models of MDT training in Africa.

- Engage university groups for youth base

- Specific research agenda

- Development of membership [using more social media?]