AfroPHC EB Meeting by Zoom 2pm CAT 1st October 2021

Present: Innocent Besigye (President), Francoise Nwabufo (Vice-President), Shabir Moosa (Executive Coordinator), Joseph Ana, Cynthia Chaibva, Tolu Osigbesan Almoghirah Abdellah, Marie-Claire Wangari, Champion Nyoni, Godwin Aja,

Apologies: Radha Karnad, Bongi Sibanda,

Absent:

Guests:

|  | Topic and discussion |
| --- | --- |
|  | AGENDA - Welcome and Introductions - Adoption of minutes - Stakeholder engagements - AfroPHC Supporting Organisations - AfroPHC Advisory Board - WHO Issues - AfroPHC Youth Hub - EC Report for noting - Policy Workshops - Management Training - Clinical Training / CPD - AfroPHC Research Group / APCC - Communication - Admin - Plan for Advisory Board Meeting - AfroPHC Strategic/Operational Plan - EC Report against Plan - Value-add for members/supporters - AOB - Next meeting / Closure |
| 1 | Welcome and introductions President welcomed all and congratulated Nigeria for its 60 years celebration. There were brief introductions by all those present. |
| 2 | Adoption of agenda, minutes and actions Minutes of 3rd September 2021 were adopted moved by Joseph Ana, seconded by Cynthia Chaibva. An amendment was that our application to HIFA was not mentioned. HIFA has not responded to our application to join HIFA nor our request for them to become an AfroPHC Supporting Organisation. Actions on issues from the last meeting are discussed as they appear in the agenda. Resolutions / Action: - Joseph Ana to follow up with HIFA on our application and request. |
| 3 | Stakeholder Engagement: Supporting Organisations EB reviewed EC report on Supporting Organisations: 58 identified, 53 Invited, 40 Responded, 30 Yes, 2 No, 9 Discussing. No response from Shannon Barkley. New prospects identified. Supporting Organisations and AB members listed on AfroPHC website. Shabir had a late reply by AHF (Anbar Ganatra). Resolutions / Action: - EB adopted recommendation for Anbar Ganatra to be added to the AB. |
|  | Stakeholder Engagement: Advisory Board EC missed one application by FAMSA (Philemon Kojo-Woode), had a late reply by AHF (Anbar Ganatra) and Bongi proposed an additional member (Edna Kimaiyo). EC recommended Africa Health Federation to include private sector with extensive high level links to fill last space on AB. Resolutions / Action: - EB adopted recommendation for Anbar Ganatra to be added to the AB. |
|  | Stakeholder Engagement: WHO CSC EB reviewed EC report.. Resolutions / Action: - EB noted report |
|  | Stakeholder Engagement: WHO EB reviewed EC report. Resolutions / Action: - EB noted EC report. |
|  | Stakeholder Engagement: AfroPHC Regional / Country Chapters Not discussed. Resolutions / Action: - EC to propose a clearer strategy at next EB meeting for Country / Regional Chapter meetings in 2022, including presenting to AB in Nov and to a general meeting in Nov / Dec 2021. |
|  | Stakeholder Engagement: IPSF MOU Not discussed but MOU signed off Resolutions / Action: |
|  | Stakeholder Engagement: AfroPHC Youth Hub EC reported progress on emails and planned meeting of youth organisations, facilitated by Marie-Claire Wangari Resolutions / Action: - Marie-Claire Wangari to provide full written report at next meeting. |
| 4 | EC Report: Policy Workshops EB reviewed EC report on policy workshops. Draft policy document not discussed. Resolutions / Action: - EB noted EC report - EC to present draft policy document on “Building the PHC team for UHC in Africa” at next meeting |
|  | EC Report: Training - Management EB reviewed EC report. Enrollee plans not discussed. Resolutions / Action: - EB noted EC report - EC to follow up with AMREF team to support enrollees. |
|  | EC Report: Training - Clinical EB reviewed EC report. Planned HIV clinical meeting not discussed. Resolutions / Action: - EC to prioritise HIV group meeting to explore clinical course process. |
|  | EC Report: Research EB reviewed EC report. Resolutions / Action: - EB noted report. |
|  | EC Report: Communication EB reviewed EC report. EC shared that press releases needed more time. Resolutions / Action: - EB noted report. |
|  | EC Report: Admin EB reviewed EC report. Concerns raised on funding sustainability. Resolutions / Action: - EB noted report. - EC to report on minimal continuing costs at next meeting |
| 5 | Plan for Advisory Board Meeting EC proposed the first AB meeting be a good set of introductions, including views on AfroPHC followed by discussions on Draft AfroPHC Strategic/Operational Plan, EC report against it, and AfroPHC membership. Resolutions / Action: - EC to circulate invitation to AB meeting and present Draft AfroPHC Strategic/Operational Plan, EC report against it, and AfroPHC membership proposal. |
| 5 | Other EC shared communications with AOSIS on partner with AfroPHC to make African Journal of Family Medicine and Primary Care an official journal and collaborate on CPD. AOSIS wanted WONCA Africa to approve. EC said that WONCA Africa is discussing. He will approach the matter with AOSIS but sensitive to WONCA Africa concerns. Resolutions / Action: - EC to continue discussions with AOSIS/WONCA Africa. |
| 6 | Close of meeting President closed with thanks. Resolutions / Action: - Next EB meeting 2-4pm CAT 5th November 2021 will be the first Advisory Board Meeting |